## Summary
Defect Summary
[5 empty] | Module Summary | Expected Date | Actual Date | Assign to
1)Admin
Total | Severity | No of defect | No. closed defect | No of open defect | a. Login Page | 18/6/2015 | 19/06/2015 | Rekha
| Sev1 |  |  |  | b. Search Employee | 19/06/2015 | 23/06/2015 | Priyam
| Sev2 |  |  |  | c. View Employee/Team/Module. | 19/06/2015 | 23/06/2015 | Vipul
| Ser3 |  |  |  | d. Pie charts showing number of employees in % based on designation,expertise and billability. | 26/06/2015 | 2015-07-01 | Deril / Jerin
Total |  |  |  |  | e. Add a new employee manually | 19/06/2015 | 22/06/2015 | Simlee
[5 empty] | f. Add a new team manually | 19/06/2015 | 24/06/2015 | Suchismitha
[5 empty] | g.Add a new module manually | 19/06/2015 | 24/06/2015 | Gunveen
[5 empty] | h. Add a new employee by excel | 24/06/2015 | 25/06/2015 | Priyam / Simlee
[5 empty] | i. Add a new team by excel | 26/06/2015 | 2015-01-07 | Priyam / Gunveen
[5 empty] | j. Add a new module by excel | 26/06/2015 | 2015-03-07 | Priyam / Vipul
[5 empty] | k. Edit/ Delete Employee | 19/06/2015 |  | Devraj/Priyam
[5 empty] | l. Edit/ Delete Team | 19/06/2015 | 25/06/2015 | Devraj / Nitin
[5 empty] | m. Edit/delete Module | 23/06/2015 | 30/05/2015 | Devraj / Nitin
[5 empty] | n. View/Search Requests raised by user | 26/06/2015 | 26/06/2015 | Rekha / Sachin
[5 empty] | o. Admin action on Request | 26/06/2015 |  | Devraj / Simlee | (Sachin / Rekha)
[5 empty] | p.1 Reports (Request) | 26/6/2015 |  | Nitin / Jerin
[5 empty] | p.2 Reports (Employee) | 2015-01-07 | 13/07/2015 | Nitin / Suchismita
[5 empty] | p.3 Reports (Module) | 2015-01-07 | 2015-10-07 | Nitin / Rekha
[5 empty] | p.4 Reports (Team) | 2015-01-07 |  | Nitin / Vipul
[5 empty] | q. Project tab | 2015-01-07 | 13/07/2015 | Priyam
[5 empty] | r.Initiatives | 2015-03-07 | 2015-08-07 | Nitin
[5 empty] | s. About Us page. | 2015-03-07 |  | Gunveen
[5 empty] | t. Contact Us. | 19/06/2015 | 22/06/2015 | Vipul
[5 empty] | u. Log out | 18/06/2015 | 22/06/2015 | Rekha
2)User
[5 empty] | a.Login Page | 19/6/2015 | 22/06/2015 | Rekha
[5 empty] | b.Sign Up Page. | 24/06/2015 | 24/06/2015 | Rekha
[5 empty] | c. Search Employee | 19/06/2015 | 23/06/2015 | Priyam
[5 empty] | d. View Employee/Team/Module. | 19/06/2015 | 23/06/2015 | Vipul
[5 empty] | e. Pie charts showing number of employees in % based on designation,expertise and billability. | 26/06/2015 | 2015-07-01 | Deril / Jerin
[5 empty] | f. Raise a new request | 24/06/2015 | 24/06/2015 | Jerin / Sachin
[5 empty] | g. View Status of the request | 24/06/2015 | 26/06/2015 | Vipul / Suchismita
[5 empty] | h.Project Page. | 2015-01-07 |  | Priyam
[5 empty] | i. Initiatives | 2015-03-07 | 2015-08-07 | Nitin
[5 empty] | j. About Us Page | 2015-03-07 |  | Gunveen
[5 empty] | k. Contact Us | 19/06/2015 | 22/06/2015 | Vipul
[5 empty] | l. Log out | 18/06/2015 | 22/06/2015 | Rekha
3) Viewer
[5 empty] | a.Login Page | 19/6/2015 | 22/06/2015 | Rekha
[5 empty] | b. SignUp Page | 24/06/2015 | 24/06/2015 | Rekha
[5 empty] | c. Project tab | 2015-01-07 |  | Priyam
[5 empty] | d. Initiatives | 2015-03-07 | 2015-08-07 | Nitin
[5 empty] | j. About Us Page | 2015-03-07 |  | Gunveen
[5 empty] | f. Contact Us. | 19/06/2015 | 22/006/2015 | Vipul
[5 empty] | g. Log out | 19/06/2015 | 22/06/2015 | Rekha

## Defects
Login As Admin
Defect No. | Severity | Priority | Expected Result | Actual Result | Module | Assigned To | Status | Comment
1 | Sev-3 | High | Page displayed should be appropriate, while searching the name in workplan tab. | Page display is inappropriate while searching the name in workplan tab. | Workplan |  | Open
2 | Sev-3 | High | Page displayed should be appropriate, while searching the name in initiative tab. | Page display is inappropriate while searching the name in initiative tab. | Initiative |  | Open
3 | Sev-1 | High | Search box should respond in the Report Tab. | Search box is not responding in the Report Tab | Report |  | Open | Fixed
4 | Sev-3 | High | In report tab, heading should be report on the page. | In report tab, heading is 'workplan' on the page. | Report |  | Open | Fixed
5 | Sev-1 | High | Links in report tab, should respond and navigate to appropriate page. | Report generated for employee and report generated for team are not responding, in Report tab. | Report |  | Open
6 | Sev-1 | High | Search box should respond in the About Us Tab. | Search box is not responding in About Us Tab | About Us |  | Open | Fixed
7 | Sev-3 | Medium | Spelling of premier should be correct. | Premier spelling is incorrect in Home Tab. | Home |  | Open
8 | Sev-2 | Medium | In About Us tab, page should not be shifting while clicking on the projects link present on the page. | In About Us tab, page is shifting while clicking on the projects link present on the page. | About Us |  | Open
9 | Sev-2 | High | Under projects link, Team details should be updated. | Under project link, team details are not updated. | Projects Link |  | Open
10 | Sev-3 | High | Header should be updated in project link (R3, Premier, E-strategy) | Header is not updated in project link(R3, Premier, E-strategy) | Projects Link |  | Open | Fixed
11 | Sev-1 | High | In Initiative tab, files should be uploaded. | In Initiative tab, files are not getting updated. | Initiative |  | Open
12 | Sev-3 | Low | Under projects link, view employees and view teams should be view employee and view team | Under project link, links are view teams and view employee | Projects Link |  | Open | Fixed
13 | Sev-3 | Low | Page should be appropriate, while clicking on E-strategy link | Page is inappropriate while clicking on E-strategy. | Projects Link |  | Open
14 | Sev-2 | High | Filter by links should not be visible while selecting clicking on Pie-chart and then search employee | Filter by links are visible while selecting clicking on Pie-chart and then search employee | Filter By |  | Open
15 | Sev-3 | High | Radio button should not be visible in the displayed list while searching employee | Radio button is visible in the displayed list while searching employee | Search Box |  | Open
16 | Sev-3 | Medium | ASE should not be highlighted while selecting the team. | ASE is highlighted while selecting the team. | Team selection |  | Open
17 | Sev-3 | Medium | Font of 'select' should be in appropriate format in employee addition link. | Font of 'select' is in inappropriate format in employee addition link | Employee Addition |  | Open
18 | Sev-1 | High | Excel sheet should validate the fields in add employee link | Excel sheet is not validating the fields in add employee link | Employee Addition |  | Open
19 | Sev-3 | High | Submit button should be right below the field in add module. | Submit button is not at right place in add module link | Module Addition |  | Open
20 | Sev-2 | High | Back button should be present in add employee, add module and add team. | Back button is not present in add employee, add module and add team. | Add Employee, add module and add team |  | Open | Pending for next phase.
21 | Sev-2 | High | Heading in excel sheet should have same heading while entering values manually in add module link | Heading in excel sheet mismatching the heading while entering values manually in add module link | Add Module, Add Employee |  | Open
22 | Sev-1 | High | Database of module should be updated while uploading through excel | Database of module is not updating while uploading through excel | Add Module, Add Employee |  | Open
23 | Sev-3 | Low | View team and view module links should be in sequence. | View team and view module links are not in sequence. | Projects Link |  | Open
24 | Sev-3 | High | The header of signup page should be updated | The header of signup page should not be updated. | Signup |  | Open | Fixed
25 | Sev-3 | Medium | Header of login page should be in appropriate format | Header of login page is in inappropriate format | Login |  | Open | Fixed
26 | Sev-1 | High | Database of module should be updated while entering manually | Database of module is not getting updated while entering manually. | Add Module, Add Employee |  | Close
27 | Sev-2 | High | Heading in excel sheet should have same heading while entering values manually in add team link | Heading in excel sheet mismatching the heading while entering values manually in add team link | Add Team |  | Open
28 | Sev-1 | High | Database of team should be updated while uploading through excel. | Database of team is not getting updated while uploading through excel | Add Team |  | Open
29 | Sev-2 | High | Mandatory fields should be '*' marked. | Mandatory fields are not '*' marked. |  |  | Open
30 | Sev-3 | Medium | In report tab, reports generated for module link, fields should be in symmetry. | In report tab, reports generated for module link, fields are in symmetry. | Report |  | Open | Fixed
31 | Sev-1 | High | In report tab, reports generated for request link, search employee box should be present. | In report tab, reports generated for request link, search employee box is not present. | Report |  | Open
32 | Sev-3 | High | In report tab, Header of report for request link should be updated. | In report tab, Header of report for request link is not updated. | Report |  | Open
33 | Sev-1 | High | In report tab, report generate for request link, generate report link, search box should be present. | In report tab, report generate for request link, generate report link, search box is not present. | Report |  | Open
34 | Sev-3 | High | In report tab, report generate for request link, generate report link, page should be appropriate. | In report tab, report generate for request link, generate report link, page is inappropriate. | Report |  | Open
35 | Sev-2 | High | In report tab, report generate for request link, project links should be present. | In report tab, report generate for request link, project links are not present. | Report |  | Open
36 | Sev-2 | Medium | In report tab, report generate for request link, report to generate request link, the links of task and links of view should not be visible. | In report tab, report generate for request link, report to generate request link, the links of task and links of view are visible. | Report |  | Open
37 | Sev-3 | Low | In workplan tab, heading, 'No OF A.S.E' should be 'No of A.S.E'. | In workplan tab, heading is 'No OF A.S.E'. | Workplan |  | Open
38 | Sev-3 | Low | In workplan tab, heading, 'Team Status' should be in middle. | In workplan tab, heading, 'Team Status' is not in middle. | Workplan |  | Open
39 | Sev-2 | High | After session time out, search box should not respond. | After session time out, search box is responding. | Session Time |  | Open
40 | Sev-2 | High | In admin tool tab, authorize employee link, page should show the result of employee while searching. | In admin tool tab, authorize employee link, page is displaying other functionality along with result. | Authorize Employee |  | Open | Fixed
41 | Sev-1 | High | Employee record should be stored in db. | Employee record is not getting stored in db. | Add-Employee |  | Close
42 | Sev-3 | Medium | Link should be highlighted while selecting link of add employee. | Links are not highlighted while selecting any. | Add-Employee |  | Open
43 | Sev-2 | High | While selecting "select" link in add team module, without choosing any radio button, page should not be navigated to other page. | While selecting "select" link in add team module, without choosing any radio button, page is navigated to other page. | Add-Team |  | Close
44 | Sev-1 | High | While selecting "select" link in add team module, without choosing any radio button, page should not be navigated to other page. | While selecting "select" link in add team module, without choosing any radio button, page is navigated to other page. | Add Employee |  | Close
45 | Sev-1 | High | While selecting "edit" link in edit team module, without choosing any radio button, page should not be navigated to other page. | While selecting "edit" link in edit team module, without choosing any radio button, page is navigated to other page. | Edit Team |  | Close
46 | Sev-3 | Low | Hi ‘Im’ Admin should not be present on home page. | Hi ‘Im’ Admin is present on home page | Home Page |  | Close
47 | Sev-3 | High | Heading “pyramid optimization” should be “Talent management tool” | Heading “pyramid optimization” is not changed to “Talent management tool” |  |  | Close
48 | Sev-2 | High | Contact us page should respond on login page, sign up page, home page of admin, and also when login as user. | Contact us page is not responding on login page, sign up page and home page of admin, also while login as user. |  |  | Close
49 | Sev-1 | High | Page should not navigate to other page, while clicking on add_employee 2-3 times on the same link. | Page is navigating to other page, while clicking on add_employee 2-3 times on the same link. | Add- Employee |  | Close
50 | Ser-1 | High | Add employee page should not ask email Id validation after entering valid address. | Add employee page is asking email Id validation even after entering valid address. | Add- Employee |  | Close
51 | Sev-2 | Medium | Logout button should be at the corner of home page. | Logout button is not at the corner of the home page. | Work-plan (raise request) |  | Open
52 | Sev-2 | High | On home page, In top view of project, selecting expertise, it should display FED, BED and QA. | On home page, In top view of project, selecting expertise, it is not displaying FED, BED and QA. | Home Page |  | Open
53 | Sev-1 | High | While selecting projects on home page, it should not navigate to project tab. | While selecting projects on home page, it is navigating to project tab. | Home Page |  | Close
54 | Sev-2 | Medium | In admin tool, if we upload wrong .xls file, it should show only one error message. | In admin tool, if we upload wrong .xls file, it is showing two error message. | Admin Tool |  | Close
55 | Sev-2 | High | In Mozilla Firefox, in admin tool, while file uploading, text box should be visible. | In Mozilla Firefox, in admin tool, while file uploading, text box is not visible. | Admin Tool |  | Close | We need to define path.
56 | Sev-1 | Low | While login as admin, in admin tool tab, in view team, when we select delete link without selecting radio button, it should not display the error message "record deleted". | While login as admin, in admin tool tab, in view team, when we select delete without selecting radio button, it should display the error message "record deleted". | Admin Tool |  | Close
57 | Sev-1 | High | Edit link should respond in project tab. | Edit link is not responding in project tab. | Project Tab |  | Close
58 | Sev-1 | High | On Admin Tool tab, under project, 'view employee' link, edit button should be responding. | On Admin Tool tab, under project, 'view employee' link, edit button is not responding. | View Employee |  | Close
59 | Sev-3 | Medium | Logout button should at the corner of home page. | Logout button is not at the corner of the home page. | Log-out |  | Close
60 | Sev-2 | Medium | Team name should be a mandatory field in edit team module. | Team name is not a mandatory field in edit team module | Edit Team |  | Close
61 | Sev-3 | Low | Font color of warning message should be green/black. | Message font color is red. | All module |  | Open | Dark Green is prefered
62 | Sev-2 | Medium | Team Id should not be visible in view team module. | Team Id is visible in view team module. | View Team |  | Close
Login As User
63 | Sev-3 | Medium | In home tab, page should be appropriate. | In home tab, page is inappropriate. | Home |  | Open
64 | Sev-3 | Medium | In home tab, primier spelling should be premier | In home tab, premier spelling is wrong. | Home |  | Open
65 | Sev-2 | High | Employee details and module details should be displayed while clicking on view employee and view module. | Employee details and module details are not displayed while clicking on view employee and view module. | View employee and view module |  | Open
66 | Sev-1 | High | In workplan tab, search field should be present. | In workplan tab, search field is not present. | Work Plan |  | Open
67 | Sev-3 | High | Workplan page display should be appropriate. | Workplan page display is inappropriate. | Work Plan |  | Open
68 | Sev-1 | High | Roll on/ Roll off process should navigate to respective page. | Roll on/ Roll off process link are not responding. | Roll On/Roll Off |  | Open
69 | Sev-3 | High | Project tab page display should be appropriate. | Project tab page display is inappropriate. | Project |  | Open
70 | Sev-1 | High | Reset button should not be missing while raising a request in work plan tab. | Reset button is missing while raising a request in work plan tab. | Work-plan (raise request) |  | Close | Reset button should be in Caps.
71 | Sev-2 | Medium | Validation of fields should be there in the work plan tab. | Validation of fields is missing in the work plan tab. | Work-plan (raise request) |  | Close
72 | Sev-1 | High | Home page tab should not be missing, while raising a request. | Home page tab is missing, while raising a request. | Work-plan (raise request) |  | Close
73 | Sev-2 | High | Click on work plan while login as user, Select raise request -> again select work plan -> it should not redirected to other link. | Click on work plan while login as user, Select raise request -> again select work plan -> it is redirecting to other link. | Work-plan (raise request) |  | Close
74 | Sev-3 | Medium | Logout page heading should be Talent Management Tool | Logout page heading is showing pyramid optimization | Log-out |  | Close
75 | Sev-1 | High | Project tab should be responding while login as user | Project tab is not responding while login as user | Project Tab |  | Close
76 | Sev-3 | Low | Font color of warning message should be green/ black. | Message font color is red. | All module |  | Open | Dark Green is prefered
77 | Sev-2 | Medium | Displayed page should not shift while clicking on the premier and R3 links. | Displayed page is shifting while clicking on the premier and R3 links. | Premier+R3 links |  | Open
78 | Sev-2 | Medium | ASE should not be highlighted when we click on project link-> R3 -> Select Team. | ASE is highlighted when we click on project link-> R3 -> Select Team. | Project link |  | Open
79 | Sev-2 | High | Radio button should not be present in the displayed list of search employee. | Radio button is present in the displayed list of search employee. | Search Box |  | Open
80 | Sev-1 | Medium | In project tab, view links should not be missing. | In project tab, view links are missing. | Project Tab |  | Open
81 | Sev-1 | Medium | Pie chart of E-Strategy on home tab, should be visible. | Pie chart of E-Strategy on home tab, is not visible. | Pie-Chart |  | Open
82 | Sev-2 | High | Pie-Chart should hold while on it. | Pie chart is keeps on changing. | Pie-Chart |  | Open
83 | Sev-2 | High | Search box should not be missing in Initiative Tab. | Search box is missing in Initiative Tab. | Search Box+Initiative Tab |  | Open
84 | Sev-3 | High | In Initiative tab, the displayed page should be appropriate. | In Initiative tab, the displayed page is inappropriate. | Initiative Tab |  | Open
85 | Sev-2 | High | In About Us Tab, details should be displayed while searching the name in search box. | In About Us Tab, details are displayed while searching the name in search box. | About Us+ Search Box |  | Open
86 | Sev-3 | High | Header of Home Tab, should be updated. | Header of Home Tab is not updated. | Home Tab |  | Open
87 | Sev-1 | Medium | In initiative tab, view links should not be missing. | In initiative tab, view links are missing. | Initiative Tab |  | Open
88 | Sev-1 | Medium | In About Us tab, view links should not be missing. | In About Us tab, view links are missing. | About Us |  | Open
Login As Viewer
89 | Sev-1 | High | Links and functionallity should not be missing while clicking on E-strategy, Premier and R3. | Links and functionallity are missing while clicking on E-strategy, Premier and R3. | Links +Home Page |  | Open
90 | Sev-3 | High | Primer spelling should be premier | Premier spelling is primier. | Premier |  | Open
91 | Sev-2 | Medium | Displayed page should not shift while clicking on the premier and R3 links. | Displayed page is shifting while clicking on the premier and R3 links. | Premier+R3 links |  | Open
92 | Sev-1 | Medium | Search box should not be visible, while clicking on the link R3, Premier | Search box is visible, while clicking on the link R3, Premier | Search Box |  | Open
93 | Sev-1 | High | Home Tab -> Premier -> Home Tab 'viewer should not be logged out' | Home Tab -> Premier -> Home Tab 'viewer is logged out' | Home Tab |  | Open
94 | Sev-1 | Medium | Pie chart of E-Strategy on home tab, should be visible. | Pie chart of E-Strategy on home tab, is not visible. | Pie-Chart |  | Open
95 | Sev-2 | Medium | ASE should not be highlighted when we click on project link-> R3 -> Select Team. | ASE is highlighted when we click on project link-> R3 -> Select Team. | Project link |  | Open

## Dummy_for_Comparison1
Defect Summary
[5 empty] | Module Summary | Expected Date | Actual Date | Assign to
1)Admin
Total | Severity | No of defect | No. closed defect | No of open defect | a. Login Page | 18/6/2015 | 19/06/2015 | Rekha
| Sev1 |  |  |  | b. Search Employee | 19/06/2015 | 23/06/2015 | Priyam
| Sev2 |  |  |  | c. View Employee/Team/Module. | 19/06/2015 | 23/06/2015 | Vipul
| Ser3 |  |  |  | d. Pie charts showing number of employees in % based on designation,expertise and billability. | 26/06/2015 | 2015-07-01 | Deril / Jerin
Total |  |  |  |  | e. Add a new employee manually | 19/06/2015 | 22/06/2015 | Simlee
[5 empty] | f. Add a new team manually | 19/06/2015 | 24/06/2015 | Suchismitha
[5 empty] | g.Add a new module manually | 19/06/2015 | 24/06/2015 | Gunveen
[5 empty] | h. Add a new employee by excel | 24/06/2015 | 25/06/2015 | Priyam / Simlee
[5 empty] | i. Add a new team by excel | 26/06/2015 | 2015-01-07 | Priyam / Gunveen
[5 empty] | j. Add a new module by excel | 26/06/2015 | 2015-03-07 | Priyam / Vipul
[5 empty] | k. Edit/ Delete Employee | 19/06/2015 |  | Devraj/Priyam
[5 empty] | l. Edit/ Delete Team | 19/06/2015 | 25/06/2015 | Devraj / Nitin
[5 empty] | m. Edit/delete Module | 23/06/2015 | 30/05/2015 | Devraj / Nitin
[5 empty] | n. View/Search Requests raised by user | 26/06/2015 | 26/06/2015 | Rekha / Sachin
[5 empty] | o. Admin action on Request | 26/06/2015 |  | Devraj / Simlee | (Sachin / Rekha)
[5 empty] | p.1 Reports (Request) | 26/6/2015 |  | Nitin / Jerin
[5 empty] | p.2 Reports (Employee) | 2015-01-07 | 13/07/2015 | Nitin / Suchismita
[5 empty] | p.3 Reports (Module) | 2015-01-07 | 2015-10-07 | Nitin / Rekha
[5 empty] | p.4 Reports (Team) | 2015-01-07 |  | Nitin / Vipul
[5 empty] | q. Project tab | 2015-01-07 | 13/07/2015 | Priyam
[5 empty] | r.Initiatives | 2015-03-07 | 2015-08-07 | Nitin
[5 empty] | s. About Us page. | 2015-03-07 |  | Gunveen
[5 empty] | t. Contact Us. | 19/06/2015 | 22/06/2015 | Vipul
[5 empty] | u. Log out | 18/06/2015 | 22/06/2015 | Rekha
2)User
[5 empty] | a.Login Page | 19/6/2015 | 22/06/2015 | Rekha
[5 empty] | b.Sign Up Page. | 24/06/2015 | 24/06/2015 | Rekha
[5 empty] | c. Search Employee | 19/06/2015 | 23/06/2015 | Priyam
[5 empty] | d. View Employee/Team/Module. | 19/06/2015 | 23/06/2015 | Vipul
[5 empty] | e. Pie charts showing number of employees in % based on designation,expertise and billability. | 26/06/2015 | 2015-07-01 | Deril / Jerin
[5 empty] | f. Raise a new request | 24/06/2015 | 24/06/2015 | Jerin / Sachin
[5 empty] | g. View Status of the request | 24/06/2015 | 26/06/2015 | Vipul / Suchismita
[5 empty] | h.Project Page. | 2015-01-07 |  | Priyam
[5 empty] | i. Initiatives | 2015-03-07 | 2015-08-07 | Nitin
[5 empty] | j. About Us Page | 2015-03-07 |  | Gunveen
[5 empty] | k. Contact Us | 19/06/2015 | 22/06/2015 | Vipul
[5 empty] | l. Log out | 18/06/2015 | 22/06/2015 | Rekha
3) Viewer
[5 empty] | a.Login Page | 19/6/2015 | 22/06/2015 | Rekha
[5 empty] | b. SignUp Page | 24/06/2015 | 24/06/2015 | Rekha
[5 empty] | c. Project tab | 2015-01-07 |  | Priyam
[5 empty] | d. Initiatives | 2015-03-07 | 2015-08-07 | Nitin
[5 empty] | j. About Us Page | 2015-03-07 |  | Gunveen
[5 empty] | f. Contact Us. | 19/06/2015 | 22/006/2015 | Vipul
[5 empty] | g. Log out | 19/06/2015 | 22/06/2015 | Rekha