## Sheet1
LOGIN AS AN ADMIN
Defect ID | Defect Description | Sevierity | Priority | Assigned to | Status | Date | ETA | Comments
1 | User is not able to navigate to contact us page from about us page | Sev2 | High |  | Closed | 2015-08-18 | 2015-08-18
2 | Contact us page is not updated in LogIN page | Sev2 | High |  | Open | 2015-08-18
3 | Error message for mismatch of username and password is incorrect | Sev2 | High |  | Open | 2015-08-18 |  | fixed
4 | Search is not working in Edit Employee page | Sev-2 | High |  | Open | 2015-08-18
5 | After search in home, for editing,validations are not there | Sev-2 | High |  | Open | 2015-08-18
6 | For deleting,validations are not there. | Sev-2 | High |  | Open | 2015-08-18 |  | Before editing,no validations
7 | Search is not working in Delete Employee page | Sev-2 | High |  | Open | 2015-08-18
8 | Search is not working in estrategy , r3 and premier pages. | Sev-2 | High |  | Open | 2015-08-18 |  | Check the pages following them.
9 | Search is not working in admintool page | Sev-2 | High |  | Open | 2015-08-18
10 | Add Employee by excel. If wrong sheet no. is entered, flow is breaking | Sev-1 | High |  | Open | 2015-08-18
11 | Add Employee by excel. If wrong file is selected, flow is breaking | Sev-1 | High |  | Closed | 2015-08-18 | 2015-08-18
12 | Add Employee manually,validations for the fields is not there | Sev-2 | High |  | Open | 2015-08-18 |  | For some fields no validations.
13 | Selecting the admintool tab, Add module should be highlighted and should be navigate to add module page | Sev-3 | Low |  | Open | 2015-08-18
14 | For search the font of name is different | Sev-3 | Low |  | Open | 2015-08-18
15 | Add Module by excel, after clicking submit button,blank page appears | Sev-1 | High |  | Open | 2015-08-18
16 | Add Module manually, fields mismatch from excel. | Sev-2 | High |  | Open | 2015-08-18
17 | AddTeam manually, fireld mismatch from excel | Sev-2 | High |  | Open | 2015-08-18
18 | AddTeam manually,search is not working | Sev-2 | High |  | Open | 2015-08-18
19 | Add Team manually, record insertion or not message is shown in addemployee page | Sev-2 | High |  | Open | 2015-08-18
20 | LCR is shown as zero in workplan tab | Sev-2 | High |  | Open | 2015-08-18
21 | Edit Current release, search is not working | Sev-2 | High |  | Open | 2015-08-18
22 | PDF is not generated and flow is breaking | Sev-1 | High |  | Open | 2015-08-18
23 | Admin is not able to see the reports for requests if he selects nothing. | Sev-2 | High |  | Open | 2015-08-18