## Sheet1
LOGIN AS AN ADMIN
Defect ID | Defect Description | Sevierity | Priority | Assigned to | Status | Date | ETA | Comments
1 | User is not able to navigate to contact us page from about us page | Sev2 | High |  | Closed | 2015-08-18 | 2015-08-18
2 | Contact us page is not updated in LogIN page | Sev2 | High |  | Closed | 2015-08-18 | 2015-08-19
3 | Error message for mismatch of username and password is incorrect | Sev2 | High |  | Closed | 2015-08-18 | 2015-08-19
4 | Search is not working in Edit Employee page | Sev-2 | High |  | fixed | 2015-08-18 | 2015-08-19
5 | After search in home, for editing,validations are not there | Sev-2 | High |  | Closed | 2015-08-18 | 2015-08-19
6 | For deleting,validations are not there. | Sev-2 | High |  | Closed | 2015-08-18 | 2015-08-19 | Before editing,no validations
7 | Search is not working in Delete Employee page | Sev-2 | High |  | fixed | 2015-08-18
8 | Search is not working in estrategy , r3 and premier pages. | Sev-2 | High |  | fixed | 2015-08-18 |  | Check the pages following them.
9 | Search is not working in admintool page | Sev-2 | High |  | Closed | 2015-08-18 | 2015-08-19
10 | Add Employee by excel. If wrong sheet no. is entered, flow is breaking | Sev-1 | High |  | fixed | 2015-08-18 |  | Exception
11 | Add Employee by excel. If wrong file is selected, flow is breaking | Sev-1 | High |  | Closed | 2015-08-18 | 2015-08-18
12 | Add Employee manually,validations for the fields is not there | Sev-2 | High |  | fixed | 2015-08-18 |  | Expertise field is mandatory and not marked
13 | Selecting the admintool tab, Add module should be highlighted and should be navigate to add module page | Sev-3 | Low |  | fixed | 2015-08-18
14 | For search the font of name is different | Sev-3 | Low |  | fixed | 2015-08-18
15 | Add Module by excel, after clicking submit button,blank page appears | Sev-1 | High |  | fixed | 2015-08-18
16 | Add Module manually, fields mismatch from excel. | Sev-2 | High |  | In progress | 2015-08-18
17 | AddTeam manually, fireld mismatch from excel | Sev-2 | High |  | In progress | 2015-08-18
18 | AddTeam manually,search is not working | Sev-2 | High |  | fixed | 2015-08-18
19 | Add Team manually, record insertion or not message is shown in addemployee page | Sev-2 | High |  | fixed | 2015-08-18
20 | LCR is shown as zero in workplan tab | Sev-2 | High |  | Closed | 2015-08-18 | 2015-08-19
21 | Edit Current release, search is not working | Sev-2 | High |  | Closed | 2015-08-18 | 2015-08-19
22 | PDF is not generated in roll off process | Sev-2 | High |  | Closed | 2015-08-18 | 2015-08-19 | in IE
23 | Admin is not able to see the reports for requests if he selects nothing. | Sev-2 | High |  | fixed | 2015-08-18
24 | Add module by excel, Validations for submit button are not there, flow breaks. | Sev-1 | High |  | fixed | 2015-08-19 |  | Exception
25 | PDF is generated in the name of the previous username or the username we used first. | Sev-2 | High |  | New/Open | 2015-08-19
26 | Add module by excel, the user is unable to insert new modules and flow breaks | Sev-1 | High |  | fixed | 2015-08-19
27 | Add team by excel, if the user enters wrong sheet no., the flow breaks | Sev-1 | High |  | fixed | 2015-08-19

## Sheet2
Status | Sev 1 | Sev 2 | Sev 3 | Total
New | 1 | 1 | 0 | 2
Open/In Progress | 4 | 9 | 2 | 15
Fixed/Retest | 0 | 0 | 0 | 0
Closed | 1 | 9 | 0 | 10
Rejected | 0 | 0 | 0 | 0
Total | 6 | 19 | 2 | 27